## Sheet1
Task Name | Assignee | Task Status | Expected time to finish | Actual time to finish
DIO | MAhmoud Sarhan | completed | 0.5 | 0.5
Timer | Hejazy |  | 0.5 | 0.5
ADC | Arafa |  | 1 | 1
Keypad | Basel |  | 1 | 1
LCD | Basel |  | 1 | 1
Buzzer | Mahmoud Sarhan | completed | 0.5 | 0.5
Temperature Sensor | Hejazy |  | 1 | 1
Timer Manager | Hejazy |  | 0.5 | 0.5
APP | Mahmoud Sarhan | completed | 1 | 1
Design Document | Mahmoud Sarhan | compeleted | 4 | 4
header files | Mahmoud Sarhan | compeleted | 1 | 1